## Cover
Work sample - fictional scenario
EA minutes & action tracker work sample
THE BRIEF
Fictional Situation | It is Mon 12 Oct 2026. The weekly leadership meeting ran 9:30–10:30 AM ET on Teams. My power went out at 9:40 AM, so I worked from the Teams auto-transcript, which had wrong speaker labels and misheard names.
Constraints | Minutes on one page, decisions and actions only. Every action has one owner and an exact day + date. HR offer details stay with HR. All times ET. Nothing goes out until Dana approves.
Deadlines | Minutes and action tracker to Dana by Mon 12 Oct, 2:00 PM ET (9:00 PM Nairobi).
Prepared by | Eddah Dena — Executive Administrative Assistant to Dana Whitfield. Status: DRAFT for Dana's approval.
MY APPROACH
1. Clean | Corrected speakers (both "Speaker" lines were Priya; the 9:35 staffing line was Luis) and names (TrailMart, Kevin Cho).
2. Extract | Pulled out the final decisions only, the actions (who, what, when) and the confidential items.
3. Reconcile | Gave A-031 to A-035 a new status and added new actions A-036 to A-043 (Action Tracker).
4. Date | Turned "Friday", "next week" etc. into day + date; flagged undated actions instead of guessing.
5. Communicate | Wrote the 1-page minutes, a draft email for Dana, the Mon 19 Oct agenda and 3 questions for Dana (Word file).
LOG
Time | About 2 hrs, including revisions after review.
Hardest call | The temp decision changed late (25 to 20 after Tom's Q3 cash point), and three speaker labels in the transcript were wrong.
What I'd change | Keep backup power for live notes so I'm not relying on the auto-transcript.
SHEETS
Cover | This page.
Action Tracker | All actions A-031 to A-043 with owner, exact due date, status and flags for Dana.
Companion file | MInutes Task 2.docx: minutes, follow-up email, Mon 19 Oct agenda, clarify with Dana, log.

## Action Tracker
Work sample - fictional scenario
Kestrel Ridge Outdoor Co.
Leadership Action Tracker
Date: as at Mon 12 Oct 2026, all times ET
ID | Owner | Action | Due (day + date) | Status | Update from 12 Oct meeting | Flag
A-031 | Marcus Reyes | Circulate revised freight contract summary | NO DATE - flag (was Fri 9 Oct) | Carried over | Raised; Marcus waiting on legal. Not revisited, no new date given. | New date needed - ask Dana
A-032 | Priya Nair | Send TrailMart deck to Dana for review | Tue 6 Oct | Done | Priya sent to Dana Wed 7 Oct; Dana confirmed receipt.
A-033 | Luis Ortega | Get 3 quotes for warehouse racking | Fri 23 Oct | In progress | 2 of 3 received; Dana extended due date from Fri 16 Oct.
A-034 | Tom Becker | Q3 close timetable to leadership | Mon 12 Oct | In progress | Overdue (was Fri 9 Oct); Tom to send today.
A-035 | Dana Whitfield | Thank-you note to board chair (Ellen) | NO DATE - flag (was Thu 8 Oct) | Carried over | Dana confirmed she will do it; no new date given. | New date needed - ask Dana
A-036 | Tom Becker | Cash flow forecast to Q2 2027 for the board (help from Marcus's team if needed) | Fri 30 Oct | Open | Dana set Fri 30 Oct (Tom asked for Fri 6 Nov).
A-037 | Dana Whitfield | Send board summary to Raj | Thu 15 Oct | Open | New.
A-038 | Priya Nair (lead); Tom Becker reviews | TrailMart spring margin impact (14 ft vs 18 ft last year) | Mon 19 Oct, before 9:30 AM ET meeting | Open | Priya leads with sell-through data; Tom checks the math.
A-039 | Priya Nair | Thank-you note to Kevin Cho (TrailMart) with Q2 end-cap proposal | Fri 16 Oct | Open | New.
A-040 | Luis Ortega | Brief agency: 20 peak-season temps from Sun 1 Nov | NO DATE - flag (must be before Sun 1 Nov) | Open | Final decision 20 temps (not 25), after Tom's Q3 cash update. | Date needed - ask Dana
A-041 | Dana Whitfield | Review whether to add the other 5 temps (Luis to bring volume data) | Sun 15 Nov - flag (falls on a Sunday) | Open | Review date as stated in meeting. | Confirm date - ask Dana
A-042 | Executive Assistant | Check calendars and propose new weekly meeting time (requested 10:00 AM ET) | Wed 14 Oct | Open | Requested by Priya (8:30 AM CT start).
A-043 | Executive Assistant | Send approved minutes and tracker to all attendees (incl. Janelle) | Mon 12 Oct, after Dana approves | Open | Nothing goes out before Dana approves.